## Week01
Dairy | Week 2 |  |  |  |  | Team Leader: | Asad Iqbal
Name of Team: | GameGrid |  |  |  |  | Team Scribe: | Idris Saifuddin
| Asad | Idris | Jawad | Shaf
Day 1 | Programming | Programming | Programming | Programming
Day 2 | Programming | Programming | Programming | Programming
Day 3 | Programming | Programming | Redesigning reports | Redesigning reports
Day 4 | Programming | Programming | Redesigning Gantt Chart | Redesigning Gantt Chart
Day 5 | Team Meeting for progress | Team Meeting for progress | Team Meeting for progress | Team Meeting for progress
Day 6 | Designing Login | Designing Login | Redesigning UML diagrams | Redesigning UML diagrams
Day 7 | Designing Login | Designing Login | Redesigning UML diagrams | Redesigning UML diagrams
| Meeting of Minutes: Week 2 meeting 1 |  |  |  | Date/Time: | 11th feb
Present / Absent: Present all.
| Agenda/issues |  |  |  |  | Resolution/Date | Next week
1 | Facing issues with packages
2 | Facing issues with firebase connectivity
3 | Issues with login
4
| Next meeting and proposed agenda | To help speed up the process of programming
making sure client database connectivity is working