## Week01
Dairy | Week 3 |  |  |  |  | Team Leader: | Asad Iqbal
Name of Team: | GameGrid |  |  |  |  | Team Scribe: | Idris Saifuddin
| Asad | Idris | Jawad | Shaf
Day 1 | Designing Login | Programming and designing website | Designing website | Designing website
Day 2 | Designing Login | Programming and designing website | Designing website | Hosting Website
Day 3 | Designing Login | Designing Login | Designing website | Designing website
Day 4 | Designing Login | Designing Login | Designing website | Designing website
Day 5 | Team Meeting for progress | Team Meeting for progress | Team Meeting for progress | Team Meeting for progress
Day 6 | Designing Login | Designing Login | Designing website | Designing website
Day 7 | Designing Login | Designing Login | Designing website | Hosting Website
| Meeting of Minutes: Week 2 meeting 1 |  |  |  | Date/Time: | 18th feb
Present / Absent: Present all.
| Agenda/issues |  |  |  |  | Resolution/Date | Next week
1 | Getting the project website up
2 | Making the login work
3 | Start desgining other GUI and program them
4
| Next meeting and proposed agenda | To help speed up the process of programming
Start designing and programming the rest of the application