## Week 4
Diary: |  | Week 4
|  |  | Team Leader: | Asad Iqbal
Name of Team: |  | GameGrid | Team Scribe: | Idris Saifuddin
| Asad | Idris | Jawad | Shaf
Day 1 | Finalizing Login/Signup screen designs | Finalizing Login/Signup screen designs | Keeping protoytypes of the app's progress so far | Documenting team's progress
Day 2 | Finalizing Login/Signup screen designs | Finalizing Login/Signup screen designs | Keeping protoytypes of the app's progress so far | Documenting team's progress
Day 3 | Setting up backend Servers | Setting up backend Servers | Keeping protoytypes of the app's progress so far | Researched about backend integration issues
Day 4 | Setting up backend Servers | Setting up backend Servers | Researched about backend integration issues | Configuring backend
Day 5 | Initiating integration of frontend with backend | Initiating integration of frontend with backend | Making sure weekly progress criteria is met | Configuring backend
Present / Absent: |  | Present all | Date/Time: | 3rd March

## Week 5
Diary: |  | Week 4
|  |  | Team Leader: | Asad Iqbal
Name of Team: |  | GameGrid | Team Scribe: | Idris Saifuddin
| Asad | Idris | Jawad | Shaf
Day 1 | Moving everything to Android studio | Moving everything to Android studio | Moving everything to Android studio | Moving everything to Android studio
Day 2 | Developing Login | Database and backend integration of firebase | Developing Forgot password | Developing sign up
Day 3 | Developing Login | Database and backend integration of firebase | Developing Forgot password | Developing sign up
Day 4 | Developing Login | Database and backend integration of firebase | Developing Forgot password | Developing sign up
Day 5 | Developing Login | Database and backend integration of firebase | Developing Forgot password | Developing sign up
Present / Absent: |  | Present all | Date/Time: Saturday | 10th March